Pixelence QMS

Development Services Line Items and Phase 1 Proposal

Prepared for: Pixelence

Basis: QMS Functional Specifications v1.2 and QMS Software Development Specification v0.1

Rate: RM 80 per hour. All amounts exclude SST unless stated.

# 1. Summary

Pixelence QMS is a web-based Quality Management System for Software as a Medical Device, covering ISO 13485, ISO 14971, IEC 62304, FDA 21 CFR Part 820/11 and EU MDR. The full specification totals 2,895 hours (RM 231,600 before SST). To fit the RM 40,000 budget, we propose a fixed-price Phase 1 covering the compliance foundation and document control, with the remaining modules delivered in later phases.

| Item | Hours | Amount (RM) |
| --- | --- | --- |
| Full scope (62 line items, incl. 10% PM) | 2,895 | 231,600 |
| Phase 1 (fixed price, excl. SST) | 500 | 40,000 |
| SST 8% on Phase 1 |  | 3,200 |
| Phase 1 total incl. SST |  | 43,200 |

# 2. Phase 1 Scope

| Item # | Line item | Hours |
| --- | --- | --- |
| 2 | Monorepo setup, isolated Next.js QMS app, CI/CD | 40 |
| 3 | Convex schema, indexes, validators | 48 |
| 4 | Authentication, RBAC, IdP/SSO and MFA | 64 |
| 5 | QMS portal shell and design system | 40 |
| 7 | Electronic signature engine | 56 |
| 8 | ESignatureModal UI | 24 |
| 9 | Immutable audit trail helper and write-mutation wrapping | 40 |
| 13 | Document lifecycle backend and versioning | 64 |
| 16 | Document UI (list, detail, review/approval, history) | 56 |
|  | Development subtotal | 432 |
|  | Project management (10%) | 43 |
|  | Phase 1 total hours | 475 |

| Phase 1 pricing | Amount (RM) |
| --- | --- |
| 475 hours at RM 80 | 38,000 |
| Reserve for basic testing and handover (about 25 hours) | 2,000 |
| Phase 1 fixed price (excl. SST) | 40,000 |
| SST 8% | 3,200 |
| Total incl. SST | 43,200 |

## Assumptions and exclusions

- The RM 40,000 is treated as excluding SST.

- Hours assume no reuse of existing code in the repository. If part of Phase 1 is already built, the scope can be extended within the same budget.

- Phase 1 includes basic testing only. Full IQ/OQ/PQ validation is part of a later phase.

- Excluded: hosting, LLM usage, third-party licences, regulatory consulting, and external audit or notified-body fees.

- The v0.1 document lists NestJS, PostgreSQL and Temporal; the newer v1.2 specification uses Convex. Estimates follow v1.2.

# 3. Full Scope Line Items

Estimated hours for the complete specification, grouped by module. Item numbers match those used in Phase 1.

## Project Foundation & Architecture

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 1 | Discovery, requirements baseline & project plan | Spec §1, §9 | 40 |
| 2 | Monorepo setup (Turborepo), isolated Next.js QMS app (port 3002), CI/CD pipeline | §2, §9 Ph.1 | 40 |
| 3 | Convex schema: 18 tables, indexes, validators, migrations | §7 | 48 |
| 4 | Authentication, RBAC (super-admin, manager, director, auditor, staff), IdP/SSO and MFA | §3; FR-001 | 64 |
| 5 | QMS portal shell: layout, navigation, responsive design system | NFR | 40 |
| 6 | Express API gateway extensions (PDF, email, e-sign verify endpoints) | §2.1 | 48 |
|  | Subtotal |  | 280 |

## Compliance Core (21 CFR Part 11 / Annex 11)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 7 | Electronic signature engine (re-auth, bcrypt verify, HMAC-SHA256, signature records) | §5.1; FR-002 | 56 |
| 8 | ESignatureModal UI with signature meaning and metadata display | §5.1 | 24 |
| 9 | Immutable audit trail: writeAuditLog helper, wrapping all write mutations, append-only enforcement | §5.2; FR-003 | 40 |
| 10 | Audit trail viewer UI (search, filter, export) | §5.2 | 24 |
| 11 | Notification service (SMTP/SendGrid email, in-app alerts) | §8 | 40 |
| 12 | Convex Scheduler workflows (review reminders, CAPA timers, escalations) | §6; Ph.3 | 48 |
|  | Subtotal |  | 232 |

## Document & Change Control (DCC)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 13 | Document lifecycle backend (draft, in-review, awaiting approval, effective, archived, obsolete) and versioning | §4.1; FR-004 | 64 |
| 14 | Change request module linked to risks, requirements and releases | FR-005 | 40 |
| 15 | Controlled PDF rendition (watermark, version stamp, signature block) and file storage | §4.1 | 40 |
| 16 | Document UI: list, detail, review/approval flow, version history | §4.1 | 56 |
| 17 | Periodic review tracking and reminders | §4.1, §4.11 | 16 |
|  | Subtotal |  | 216 |

## Training Management (TM)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 18 | Training programs and role-based curricula | §4.2 | 32 |
| 19 | Quiz/assessment engine with configurable passing score | §4.2 | 40 |
| 20 | Training records, status state machine, auto-retraining on new SOP version | §4.2 | 32 |
| 21 | Clinical portal gating (block critical actions on lapsed training) | §4.2, §9 Ph.3 | 40 |
|  | Subtotal |  | 144 |

## Requirements & Traceability (RT)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 22 | Requirements registry and hierarchy (PRD, SRS, specs, tests) | §4.3 | 40 |
| 23 | Bi-directional trace links, traceability matrix and orphan detection | §4.3 | 56 |
| 24 | GitHub/GitLab integration (commit/PR linking) | §4.3, §8 | 56 |
| 25 | Traceability matrix/graph UI | §9 Ph.4 | 48 |
|  | Subtotal |  | 200 |

## Risk Management (ISO 14971)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 26 | Hazard register and FMEA scoring (S/P/D, RPN) | §4.4; FR-006 | 48 |
| 27 | Mitigation linkage to SRS and tests; residual risk computation | §4.4 | 32 |
| 28 | Risk UI with FMEA calculator and risk matrix | §9 Ph.4 | 32 |
|  | Subtotal |  | 112 |

## Design & Development Control (Digital DHF)

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 29 | DHF projects and phase management (planning to design transfer) | §4.5; FR-007 | 48 |
| 30 | DHF items (inputs, outputs, V&V) with linkage and status | §4.5 | 40 |
| 31 | Design review multi-user sign-offs and phase locking | §4.5 | 40 |
| 32 | DHF UI and package export | §4.5 | 48 |
|  | Subtotal |  | 176 |

## CAPA & Nonconformance

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 33 | Nonconformance capture and containment | §4.6 | 32 |
| 34 | CAPA workflow with action items (initiation to closure) | §4.6; FR-008 | 48 |
| 35 | Root cause tooling (5 Whys, Ishikawa diagram) | §4.6 | 40 |
| 36 | Effectiveness verification via scheduler (e.g. 60 days) and sign-off | §6.2 | 24 |
| 37 | CAPA UI | §9 Ph.4 | 40 |
|  | Subtotal |  | 184 |

## Supplier Quality Management

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 38 | Supplier registry, criticality and Approved Supplier List | §4.7; FR-009 | 32 |
| 39 | SCAR workflow with vendor-facing upload portal | §4.7 | 56 |
| 40 | Periodic supplier review, scoring and certificate expiry alerts | FR-009 | 24 |
|  | Subtotal |  | 112 |

## Complaint Handling & PMS

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 41 | Complaint intake and 'Report Inaccuracy' loop from clinical portal | §4.8; FR-010 | 40 |
| 42 | MDR/Vigilance decision tree with 15/30-day deadline tracking | §4.8 | 40 |
| 43 | PMS trend analysis and complaint-to-CAPA linkage | §4.8 | 40 |
|  | Subtotal |  | 120 |

## Audits & Management Review

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 44 | Audit scheduling, checklists and auditor assignment | §4.9 | 40 |
| 45 | Findings registry with auto-CAPA for major findings | §4.9; FR-011 | 24 |
| 46 | Management review: agenda, minutes, follow-up actions | §4.9 | 40 |
|  | Subtotal |  | 104 |

## AI Copilot

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 47 | LLM gateway (Vertex AI/OpenAI), prompt guardrails, usage logging | §4.10; ISO 42001 | 32 |
| 48 | SOP draft generator | §4.10; FR-013 | 40 |
| 49 | Risk assessment helper (hazard suggestions) | §4.10 | 40 |
| 50 | Traceability auditor (gap analysis) | §4.10 | 32 |
|  | Subtotal |  | 144 |

## Reporting, Dashboard & Administration

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 51 | CAPA dashboard | §4.11 | 32 |
| 52 | Document matrix | §4.11 | 16 |
| 53 | Executive review dashboard (KPIs, training compliance, audits, complaints) | §4.11; FR-012 | 40 |
| 54 | Home dashboard | Spec §4 | 24 |
| 55 | Administration (users, roles, configuration) | Spec §4 | 40 |
|  | Subtotal |  | 152 |

## Verification, Validation & Release

| # | Line item | Spec ref | Hours |
| --- | --- | --- | --- |
| 56 | Automated testing (unit, integration, E2E) per module | Spec §10 | 160 |
| 57 | Computer system validation documentation (IQ/OQ/PQ, IEC 62304 and Part 11 evidence) | §1.1 | 120 |
| 58 | Security and penetration testing, encryption review | NFR | 40 |
| 59 | Data seeding and migration of existing quality records | - | 24 |
| 60 | UAT support and defect remediation | UAT-Test-Plan.md | 40 |
| 61 | Production deployment, monitoring, hardening | NFR 99.9% | 40 |
| 62 | User documentation and training | - | 32 |
|  | Subtotal |  | 456 |

# 4. Full Scope Summary

|  | Hours |
| --- | --- |
| Development subtotal | 2,632 |
| Project management and QA oversight (10%) | 263 |
| Total | 2,895 |

At RM 80 per hour: RM 231,600 before SST, RM 18,528 SST, RM 250,128 in total.